## MAUI-MVVM
Attendance Project
S. NO. | Steps | Estimated Hours | Worked Hours
1 | Understand the flow and Process of API calling (and Doubt Clearification) | 2 | 1
2 | Code Implimentation -
Step 1:- | Creating Page to import Excel data File to Database | 6 | 12
Step 2:- | Creating Scaffolding for Model Classes | 3 | 2
Step 3:- | Creating Report functions | 8 | 7
Step 4:- | For Log Writing We Add Log Process In all above three Steps according to the conditions and looping and Log process will work Simultaneously in all the process | 8 | 7
Step 5:- | For UI Message we will show and Update the messages according to the above functionality. | 4 | 2
3 | Testing all the Minor Steps and all the major Steps one by one and then final testing | 6
Total |  | 37 | 66
Hours Remain
Day worked
Mon, wed, thru, fri 11 to 6
| 7+7+7+7 | 28
30-06-2023, 3 july,4 july ,10 july,11 july
| 7+7+7+7 | 28
| total | 66